## Sheet1
Project plan - Team Infinity
Online Long Journey Bus Reservation System
| July |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February
| 1 | 2 | 3 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3
Requirement gathering and finalizing the project scope
Studying the required technologies
Project proposal and the SRS submission
Design Structural and behavioural diagrams
Design wireframes (Both mobile and web)
Implement UI designs
Interim report submission
Database design
Completing backend
Completing non-functional requirements
UI adjustments
Quality assurance
Final report submission